## Introduction
Major projects climate risk assessment toolkit
v1
This workbook has been developed by Sniffer and Adaptation Scotland as part of the Climate Ready Clyde Accelerator programme. It is designed to support partners to assess the resilience of projects to current climate and future climate change.
The tool is divided as follows:
User Guide - An overview of how to use this workbook, relevant technical standards and guidance, and rough amounts of effort at each stage
Analysis flowchart - A diagram showing how the different modules relate to project design stages
Project information: Broad background information about your project
Module 1: Sensitivity Assessment - To assess how sensitive the project is to a range of climate variables
Module 2: Exposure Assessment - To assess the exposure of the project to current and future climate change
Module 3: Vulnerability Assessment - A module to view the overall vulnerability of the project, based on the outputs of module 1 and module 2
Module 4: Risk Analysis - A template to assess the key risks to your project arising from the vulnerabilities identified
Glossary - A summary of terms and their meaning used throughout this assessment workbook
The toolkit is based on the EU non-paper guidelines for project managers on making vulnerable investments climate resilient (available here: http://climate-adapt.eea.europa.eu/metadata/guidances/non-paper-guidelines-for-project-managers-making-vulnerable-investments-climate-resilient ).
All contents of this workbook © Sniffer, 2017, and may not be reproduced or modified without permission.
Sniffer is grateful to East Dunbartonshire Council, University of Strathclyde, Stirling Council and the Scottish Cities Allliance for their support in development of this tool.
Development of the tool has been funded by Scottish Government.

## User Guide
User Guide
How to use this workbook
This workbook has been designed to support you in your assessment of climate change vunerabilities and risks in infrastructure and built environment projects. It has been designed to be used with the guidance report "A Chaning Climate for Urban Developments" by Climate Ready Clyde, Adaptation Scotland and Sniffer. The guidance contains a mini-risk assessment template, designed to only take a summary view of climate risks in the early stages of project development. This workbook provides a more detailed version, which should be conducted when more detail about the project is known. The 'analysis flowchart' worksheet shows how these integrate with the project development cycle, and the RIBA plan of work 2013. The workbook has been designed to allow practitioners to assess a wide range of climatic changes. However, given the wide range of variables included, Sniffer suggest that sustainability specialists define the variables in scope of the assessment based on their particular project, and general research on the main ways in which they may be affected, prior to engaging others in the wider assessment process. The process assumes a standard level of 'adaptive capacity' (the ability to prepare, respond and recover) in a project, because the design and delivery of infrastructure or the built environment offers limited opportunities to change this. However, the ability of individuals to prepare, respond and recover to extreme weather events and climate change is significant, and should be considered as part of a more holistic aproach to managing risk.
Assesment process
The steps taken are set out in the flow chart below.
Time Requirements
The amount of time needed to conduct an assesment will vary based on a range of factors, including prior knowledge of climate change, how it impacts on the sector under consinderation, and pre-existing work. However, the below table gives some rough estimates of the time required. Note this does not include the time required to assemble the relevant information to assess your project.
Detailed Level
| Project information | 30 minutes
| Vulnerability Assessment | 1 day
| Exposure Assessment | 1 day
| Climate Risk Assessment | 1 hour
| Project Impacts / Risk Register | 1/2 day workshop
Scoring Risks
Scoring risks in Module 4 uses a 5x5 matrix in line with EU guidelines, as set out below: A more detailed set of criteria against which to judge likelihood and consequences of risks are included in p.40 - 41 of the EU guidelines for project managers.
Useful guidance
To support you in your assessments the following pieces of guidance or tools may also be helpful:
● "A changing climate for urban development" is available to download at www.climatereadyclyde.org.uk
Exposure
● UK Climate Projections 2009 - A range of guidance on how the climate will change through to 2080 under different emissions scenarios are available at https://www.metoffice.gov.uk/research/collaboration/ukcp
● SEPA Technical Flood Risk Guidance for stakeholders: http://www.sepa.org.uk/media/162602/ss-nfr-p-002-technical-flood-risk-guidance-for-stakeholders.pdf
● SEPA Flood Risk Maps - http://www.sepa.org.uk/environment/water/flooding/flood-maps/
● HSE guidance on managing workplace temperature: http://www.hse.gov.uk/temperature/thermal/managers.htm
● Design for Future Climate - Report from InnovateUK setting out design principles for adapting buildings to climate change. Supported by 40 real world case studies exploring the changes needed to designs to be climate-ready. http://www.arcc-network.org.uk/design-for-future-climate/
Sensitivity
● Flood Disadvantage in Scotland: http://www.gov.scot/Publications/2015/12/9621 - This dataset shows social and economic factors will affect the population's experience of all flooding types under a range of different flood return periods, accounting for climate change.
● CIBSE Weather Data sets - These datasets include Design Summer Years and Test Reference Years under climate change scenarios, allowing users to see how climate change will affect thermal comfort, and heating and cooling demands, allowing changes to be implemented. http://www.cibse.org/knowledge/cibse-weather-data-sets [Note - freely available datasets from University of Exeter may still be avialable here: http://emps.exeter.ac.uk/engineering/research/cee/research/prometheus/downloads/
● Care Provision Fit for a Future Climate - JRF report exploring the gap between climate modelling on overheating and the reality in the care sector, with strategies on how to overcome them in the design and operation https://www.jrf.org.uk/report/care-provision-fit-future-climate
1. Enter project information
3. Assess vulnerability of key activities
to climate variables
4. Assess exposure of key locations to climate variables
5. Rank climate risks on matrix
6. Assess potential impacts and adaptation options for greatest climate-related project risks
2. Select variables in scope

## Analysis flowchart
Analysis flowchart
The diagram below outlines the relationship between the cliamte resilience analysis stages and the aim and processes of a project more generally:
RIBA phase | Business case / governance | Risk assessment | Adaptation options | (Adaptation plan)
0 - Strategic Definition
1 – Preparation and brief
2 – Concept Design
3 – Developed design (and costing)
4 – Technical Design
5 – Construction
6 – Hand over and Close Out
7 – In Use
8 – Decommissioning
High level consideration of issues
Detailed Climate Impact Assessment
Outline adaptation strategy
Definine future climate parameters in initial design brief

## Project Information
Project Information
This section should be used to enter basic information about your project to support the assessment process.
| Project Name: |  |  |  |  | Project Type: | Non domestic building(s)
| Budget |  |  |  |  | Partners:
Description of planned investment
| Stage of project at time of assessment | [6 empty] | Date completed:
| Estimated completion date | [6 empty] | Assesment Horizon | Select a time period | The time period used for assessing climate change resilience
| Planned lifetime of investment |  |  | 50 |  |  | Enter the approximate number of years the project will be in existence once completed
| Project Scope |  | Use the dropdown features to define your project scope. This will help in applying the modules of the project
| Landscaping | Yes |  | Buildings | Non-Domestic
Energy
Contact Details
| Project Manager |  |  |  |  | Climate Resilience Assessor
| Telephone No |  |  |  |  | Telephone No.
| Email |  |  |  |  | Email
Associated evidence which supports the assessment
The following evidence has been used to support your assumptions in the development and delivery of the project

## 1. Critical Elements
STEP 1: Listing project critical elements
This should be a comprehensive list of all the elements critical to the functioning of your project. After listing every single element you can limit the extent of your risk assessment by only chosing to copy the most important elements to the vulnerability assessment.
On-site assets and processes
Teaching
Providing a public meeting place
Researching
etc.
Inputs
Students
Energy
Water
etc.
Outputs
Producing lab results
Producing research
etc.
Transport links
Commuting by Subway
Commuting by bus
Commuting by bicycle
Commuting at foot
etc.
Note on B4: Note: The physical assets on the site itself, as well activities undertaken on the site (e.g care provision, teaching)
Note on B9: Note: The materials, and resources that will be used by the site in its functioning (e.g. energy, water, but also supplies and services)
Note on B15: Guidance note: Products produced, outcomes or revenue
Note on B21: René Lindsay: The way in which users access the site (private transport, bus, rail, cycling, air)

## 2. Vulnerability
Module 1: Vulnerability of activities related to the project
Project Name
Consider to what degree the critical elements and key activities in your project are vulnerable to (affected by and unable to cope with) changing weather conditions and climate hazards.
Project Type:
Climate vulnerability |  | LOW |  |  | MED |  |  | HIGH |  |  | UNKNOWN
N.B. Where relevant, add comments on your rationale or assumptions (e.g. previous experiences that you've observed)
Key activities related to your project | Sunlight | Heatwaves | Extremely hot days | Cold winters | Extremely cold days | Urban heat islands | Changing growing seasons | Rainfall | River flooding | Surface water flooding | Sewer flooding | High humidity | Snowfall | Storms | High average wind speeds | Poor air quality | Dust storms | Landslides | Soil erosion | Soil salinity | Ocean acidification | Coastal flooding | *N.B. the person in charge of the risk assessment can modify the list to only include relevant climate hazards. There is no reason to waste time on assessing vulnerability to Ocean PH changes if it falls completely outside the purpose of your project
On-site assets and processes
Teaching | L | H | H | M | L | L | L | L | L | L | L | L | L | L | L | L | L | L | L | L | L | L
Providing a public meeting place
etc.
Shielding assets
Inputs
Students
Energy
Water
etc.
Outputs
Producing lab results
Producing research
etc.
Transport links
Commuting by Subway
Commuting by bus
Commuting by bicycle
Commuting at foot
etc.
Average | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1=Low, 2=Medium, 3=High
Summary of sensitivity
Assumptions and Evidence
Areas for further investigation
Note on A3: Kit England: There are more detailed descriptions for these if we want to add them?
Note on A11: Note: The physical assets on the site itself, as well activities undertaken on the site (e.g care provision, teaching)
Note on A22: Note: The materials, and resources that will be used by the site in its functioning (e.g. energy, water, but also supplies and services)
Note on A33: Guidance note: Products produced, outcomes or revenue
Note on A44: René Lindsay: The way in which users access the site (private transport, bus, rail, cycling, air)

## 3. Exposure
Module 2. Exposure of project location(s)
1) Consider how exposed the location of your project is to changing weather conditions and climate hazards. This is purely an assessment of whether the listed condition could occur in your location and should be listed as "Direct Exposure". 2) Make an assessment of the current level of exposure and assess the potential exposure based on current climate change projections. 3) While most critical elements and key activitires related to your project are likely to be within your own plot, remember to also assess the level of exposure of the most important external activities, inputs and transport links. This assessment should be listed as "Indirect Exposure".
2a. Direct exposure to climate hazards |  | Period covered: | Select a time period
Exposure of the location of your project | Today | In the future | Data sources used for assessment
Heatwaves | L | M
Extremely hot days | L | M
Cold winters | H | M
River flooding | L | L | SEPA
Surface water flooding | L | M | SEPA
Snowfall | M | M | UKCP18
Storms | M | M
Poor air quality | M | H
Landslides | L | L
Coastal flooding
Urban heat islands | L | M
Changing growing seasons | L | M
Extremely cold days | M | L
(select issue)
2b. Indirect exposure
Glasgow-Edinburgh railway | Rating | Rating | Data sources used for assessment
Heatwaves | L | M
Extremely hot days | L | M
Rainfall | M | M
River flooding | L | M
(select issue)
(select issue)
Power supply | Rating | Rating | Data sources used for assessment
Heatwaves | L | M
Extremely hot days | L | M
Cold winters | H | M
River flooding | L | M
(select issue)
(select issue)
Definition of exposure standards
Decide what comprises high, medium and low ratings for exposure, if not already identified in the datasets
This should include past records, experience of impacts on similar projects, critical thresholds from design standards
Safety margins/tolerances
High exposure
Medium exposure
Low exposure

## 4. Climate Risks
Module 3. Define Climate Risks
Use this template to plot the outputs of your vulnerability and exposure assessments. This will give you a view on the most important climate hazards - now and in the future - that you should address in your project or adaptation plan.
|  | 3a - Climate risks today | [8 empty] | 3b Climate risks in the future |  |  |  | Time Period: | Select a time period
|  | High | Heatwaves Extremely hot days | [7 empty] | High |  | Heatwaves Extremely hot days
| Vulnerability | Medium |  |  |  |  | Cold winters |  |  | Vulnerability | Medium |  | Cold winters
|  | Low | Urban heat islands Changing growing seasons River flooding Surface water flooding Landslides | Extremely cold days Snowfall Storms Poor air quality | [6 empty] | Low | Extremely cold days River flooding Landslides | Urban heat islands Changing growing seasons Surface water flooding Snowfall Storms |  |  | Poor air quality
|  |  | Low | Medium |  |  | High |  |  |  |  | Low | Medium |  |  | High
[5 empty] | Exposure | [8 empty] | Exposure
Relevant notes / commentary
[5 empty] | Vulnerability | Exposure 1 | Exp 2 | Exp3 | Exp total |  |  |  |  | Vulnerability | Exposure
|  | Sunlight |  | 1 | L | N/A | L | L | 1 |  |  |  |  | L | N/A
|  | Heatwaves |  | 3 | H | L | L | N/A | 1 |  |  |  |  | H | M
|  | Extremely hot days |  | 3 | H | L | L | N/A | 1 |  |  |  |  | H | M
|  | Cold winters |  | 2 | M | H | N/A | N/A | 3 |  |  |  |  | M | M
|  | Extremely cold days |  | 1 | L | M | N/A | N/A | 2 |  |  |  |  | L | L
|  | Urban heat islands |  | 1 | L | L | N/A | N/A | 0 |  |  |  |  | L | M
|  | Changing growing seasons |  | 1 | L | L | N/A | N/A | 0 |  |  |  |  | L | M
|  | Rainfall |  | 1 | L | N/A | M | N/A | 2 |  |  |  |  | L | N/A
|  | River flooding |  | 1 | L | L | L | N/A | 1 |  |  |  |  | L | L
|  | Surface water flooding |  | 1 | L | L | N/A | N/A | 0 |  |  |  |  | L | M
|  | Sewer flooding |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | High humidity |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | Snowfall |  | 1 | L | M | N/A | N/A | 2 |  |  |  |  | L | M
|  | Storms |  | 1 | L | M | N/A | N/A | 2 |  |  |  |  | L | M
|  | High average wind speeds |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | Poor air quality |  | 1 | L | M | N/A | N/A | 2 |  |  |  |  | L | H
|  | Dust storms |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | Landslides |  | 1 | L | L | N/A | N/A | 0 |  |  |  |  | L | L
|  | Soil erosion |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | Soil salinity |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | Ocean acidification |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A
|  | Coastal flooding |  | 1 | L | N/A | N/A | N/A | 0 |  |  |  |  | L | N/A

## 5. Project Impacts
Module 4: Impact Assessment
Project: | Western Infirmary project |  | Last reviewed:
Completed by: | xx
Completed on: | xx
|  | Risk score |  |  |  | Future risk | Select a time period
Climate hazard | Potential Impact | Consequence | Likelihood | Score | Controls | Consequence | Likelihood | Score | Futher action needed | Risk Owner
(select issue) | [Enter risk arising from vulnerability] |  |  | 0 |  |  |  | 0 | Enter what further action is needed to address risk | Enter owner
Surface water flooding | Damage to inventory | 4 | 3 | 12 |  | 4 | 4 | 16 | Ensure buildings are flood proof | UoG
Surface water flooding | Long term damage to construction | 5 | 2 | 10 |  | 5 | 2 | 10 | Drainage strategy
Surface water flooding | Sewer flooding hampers acces to building/affects electricity provision | 5 | 3 | 15 |  | 5 | 3 | 15 | Ensure drainage capacity | Scottish Water/UoG
Snowfall | Key transport links closed and employees/students cannot arrive | 4 | 2 | 8 |  | 4 | 2 | 8 | Ensure contingency plan available for clearing tracks | Scotrail/SPT
Heatwaves | Ability to maintain indoor comfort temperature | 3 | 1 | 3 |  | 3 | 2 | 6 |  | UoG
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0

## Glossary
Glossary
The following terms are used within the assessment process
Exposure - refers to the presence of people, livelihoods, species or ecosystems, environmental services, resources, infrastructure, or economic assets, social, or cultural sites that could be affected or adversely impacted by an extreme weather event or climatic change.
Inputs - The materials and resources that will be used by the project as its developed, and once finished, in the day to day operation (e.g. energy, water), as well as supply chains and services
On-site assets or processes - The activities that take place, or the physical assets located on the site itself. Both will vary depending on the nature of the project. Examples of activities that take place could include care provision, teaching, or leisure activities, whilst physical assets could include landscaping, laboratories, classrooms, or production lines.
Outputs - The products produced, outcomes or revenue from the activity on the site. This would cover both physical products, but also things such as learning outcomes.
Risk Asssesment - The range of detailed possible problems that could arise from the vulnerabilities identified - e.g. operational, financial, repuational, categorised by the likelihood and consequences of happening
Sensitivity - is the degree in which a system or species is affected in a positive or negative way by the variability of the climate variables.
Transport links - All methods of transport used for goods, services and individuals to get on and off the site. Can be both direct (e.g. access roads), and wider (e.g. busses and multimodal transport across a city)
Vulnerability - The combination of both sensitivity of a project and the likelihood of exposure.

## Dropdown Options or List
Tool Configuration
Project Scope
Exposure Assessment |  |  | Sensitivity Assessment |  |  | Landscaping | Buildings |  | Energy |  | Climate Variables
Select rating | [10 empty] | (select issue)
Sunlight
H |  |  | H |  |  | Yes |  |  | Yes |  | Heatwaves
M |  |  | M |  |  | No | No |  | No |  | Extremely hot days
L |  |  | L |  |  |  | Domestic |  |  |  | Cold winters
[7 empty] | Non-Domestic |  |  |  | Extremely cold days
ExposureList2' |  |  | SA' |  |  |  | Mixed - Primarily Domestic |  |  |  | Urban heat islands
[7 empty] | Mixed - Primarily Non-Domestic |  |  |  | Changing growing seasons
Rainfall
Time Periods | [10 empty] | River flooding
Select a time period | [5 empty] | Project Type |  |  |  |  | Surface water flooding
2020s (2010-2039) | [10 empty] | Sewer flooding
2030s (2020-2049) | [5 empty] | Domestic Building(s) |  |  |  |  | High humidity
2040s (2030 - 2059) | [5 empty] | Energy |  |  |  |  | Snowfall
2050s (2040 - 2069) | [5 empty] | Mixed use development |  |  |  |  | Storms
2060s (2050 - 2079) | [5 empty] | Non domestic building(s) |  |  |  |  | High average wind speeds
2070s (2060 - 2089) | [5 empty] | Non domestic building(s) - Care Home |  |  |  |  | Poor air quality
2080s (2070 - 2099) | [10 empty] | Dust storms
TimPer' | [10 empty] | Landslides
Soil erosion
Soil salinity
Risk Matrix | [10 empty] | Ocean acidification
Coastal flooding
Consequences
|  | 1 | 2 | 3 | 4 | 5 | Consequences |  | Likelihood
| 1 | 1 | 2 | 3 | 4 | 5 | 1 | Insignificant | 1 | Rare
| 2 | 2 | 4 | 6 | 8 | 10 | 2 | Minor | 2 | Unlikely
| 3 | 3 | 6 | 9 | 12 | 15 | 3 | Moderate | 3 | Moderate
| 4 | 4 | 8 | 12 | 16 | 20 | 4 | Major | 4 | Likely
| 5 | 5 | 10 | 15 | 20 | 25 | 5 | Catastrophic | 5 | Almost certain
Likelihood